## Cover
Version 1.2
2018-08-09
Overall sprint plan_Project example

## XXX Project_MediumSchedule
|  |  | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4
|  |  | 2016-10-27 | 2016-11-03 | 2016-11-10 | 2016-11-17 | 2016-11-24 | 2016-12-01 | 2016-12-08 | 2016-12-15 | 2016-12-22 | 2016-12-29 | 2017-01-05 | 2017-01-12 | 2017-01-19 | 2017-01-26 | 2017-02-02
Development of common functions
Environment building/introduction of basic functions | bar: 2016-10-27 to 2016-11-17
Building of local development environment | bar: 2016-10-27
Introduction of authentication functions | bar: 2016-11-10 to 2016-11-17
Introduction of authorization function | bar: 2016-11-10 to 2016-11-17
Screen design/UI components | bar: 2016-10-27 to 2016-12-22
Basic input components | bar: 2016-10-27 to 2016-11-03
Accordion | bar: 2016-10-27 to 2016-11-03
Year/month/day and year/month input components | bar: 2016-10-27 to 2016-11-03
Combo box input components | bar: 2016-11-10 to 2016-11-17
Category selection input components | bar: 2016-11-10 to 2016-11-17
Error notification components | bar: 2016-11-24 to 2016-12-01
Table display components | bar: 2016-11-24 to 2016-12-01
Graph display components | bar: 2016-12-08 to 2016-12-15
Side menu components | bar: 2016-12-08 to 2016-12-15
Header components | bar: 2016-12-08 to 2016-12-15
JSON API | bar: 2016-11-10 to 2016-12-08
JSON requests | bar: 2016-11-10 to 2016-11-17
JSON responses | bar: 2016-11-24 to 2016-12-01
Login/menus | bar: 2016-11-10 to 2016-12-08
Login screen | bar: 2016-11-10 to 2016-11-17
Side menu management | bar: 2016-11-24 to 2016-12-01
Master maintenance screen | bar: 2016-12-15 to 2016-12-22
Screen template | bar: 2016-12-15 to 2016-12-22
Initial display | bar: 2016-12-15 to 2016-12-22
Update process | bar: 2016-12-15 to 2016-12-22
User management/authority management screens | bar: 2017-01-05 to 2017-01-19
User registration | bar: 2017-01-05 to 2017-01-12
Updating/deleting users | bar: 2017-01-05 to 2017-01-12
Group registrations | bar: 2017-01-12 to 2017-01-19
Updating/deleting groups | bar: 2017-01-12 to 2017-01-19
Document preparation | bar: 2017-01-19 to 2017-01-26
Implementation guide | bar: 2017-01-19 to 2017-01-26
Common function documents | bar: 2017-01-19 to 2017-01-26
Application development
Application development | bar: 2016-12-15 to 2016-12-22; 2017-01-05 to 2017-01-19
XXX registration screen | bar: 2016-12-22; 2017-01-05
YYY registration screen | bar: 2016-12-22; 2017-01-05
ZZZ list display screen | bar: 2016-12-22; 2017-01-05
Master screen | bar: 2016-12-22; 2017-01-05
Final acceptance | bar: 2017-01-26
Internal quality confirmation testing | bar: 2017-01-12 to 2017-01-26
Building of development environment
Application server | bar: 2016-10-27 to 2016-11-03
Databases | bar: 2016-10-27 to 2016-11-03
Creation of repository for configuration management | bar: 2016-10-27 to 2016-11-03
Build and release settings | bar: 2016-11-10 to 2016-11-17
Confirmation of basic implementation policies
Confirmation of screen layout and design
Completion of implementation of basic parts
Completion of development